## Slide 1
ESRF-EBS : Mise en œuvre et mise en service, performance et redémarrage de l'exploitation utilisateurs
Jean-Luc Revol
On behalf of the ESRF Accelerator and Source Division

## Slide 2: outline
The ESRF-EBS project
Implementation and start-up
Commissioning and restart of user operation
COVID-19 pandemic: impact and lessons learnt

## Slide 3: ESRF facts and figures
Light source in operation since 1994
Located in Grenoble, France
22 partner nations
Annual budget: 100 million euros
Staff: 650
E- Linac
200 MeV
Booster synchrotron
300m, 4Hz
The ESRF Extremely Brilliant Source upgrade :
Decrease the horizontal emittance
Increase the source brilliance
Increase the source coherence
Storage Ring
6 GeV
32 cells

## Slide 4: The ESRF-EBS upgrade
 | Units | ESRF | ESRF-EBS
Energy | GeV | 6 | 6
Circumference | m | 844.4 | 844
Lattice |  | DBA | HMBA
Current | mA | 200 | 200
Lifetime | h | 50 | 25
Emittance H | pm.rad | 4000 | 133
Emittance V | pm.rad | 4 | 10*
31 magnets per cell instead of 17

## Slide 5: ESRF-EBS project implementation
October 2017 Start of girder assembly
10 December 2018 End USM, start shutdown
Dismantling
Installation
8 November 2019 Tunnel closed
Tests & Injector restart
28 November 2019 Accelerator commissioning
2 March 2020 Beamline commissioning
25 August 2020 Start User Mode Operation
Mock-up (Summer 2017)
Old ESRF-Storage Ring
ESRF-EBS

## Slide 6: ESRF-EBS: Installation in the tunnel
Old ESRF-Storage Ring
ESRF-EBS
Civil work
Dismantling
Dismantling
Entering girders
Moving girders
Girder in place
Interconnection & alignment
Piping
Cabling
Injection zone
Radiofrequency
Straight section for IDs
Front ends
December 2018
November 2019

## Slide 7: ESRF-EBS: Commissioning
15th December Accumulation
6th December Beam stored
28th November
First turns
30th January First Beam on 26 Beamlines
28th February
200 mA achieved
Courtesy S Liuzzo

## Slide 8: ESRF-EBS: Equipment commissioning
Low and high level control for all equipment (including vacuum):
 Started as soon as the cabling is done
Radio frequency
Power supplies
Power test of the magnets from August to November with tunnel not accessible
Injection elements
Injector
Control software, optics tools, commissioning scripts validated prior and during shutdown on the Storage Ring simulator
During last weeks of the shutdown with tunnel close (14/10 to 28/11):
  Final alignment & survey
  Validation of the personal safety system
  Global power test of the magnets
  Interlocks
  Injection/extraction elements
  Radio-frequency power commissioning
  Injector commissioning

## Slide 9: ESRF-EBS: beam Commissioning obstacles
3 physical obstacles on the beam path found during commissioning.
Detected, get around, resolved by:
Very useful beam loss and turn by turn BPM diagnostics
Bumps, non-closed injection bump, off-energy operation, distorted close orbit,,…
Intervention to remove the obstacles one by one
Largely beneficial to injection efficiency, lifetime, optics tuning
Piece of wire accidently into SS-23 ID chamber
Installation mistake Cell8-Bellow 9-11
Obstacle in Cell-5 Ch7
AL piece fall during installation of DQ2
Nominal position
Installation error in cell8

## Slide 10: ESRF-EBS: beam Commissioning vacuum issue
A Few ID NEG coated ID chambers with poor vacuum
Detected, resolved by:
Very useful beam loss diagnostics for detection
Intervention to exchange the chamber
Lifetime increase by a factor 3
Replacement
Reactivation
ID12 was contaminated  poor vacuum replaced

## Slide 11: ESRF-EBS: beam Commissioning optics tuning
Optics tuning:
Optics correction (magnet modeling) Add magnetic cross talk between adjacent magnets Correct wrong calibration factor Excellent alignment of components(<50 mm in both plane)
Orbit steering Beam base alignment (100mm rms both plane) Eigen vector optimization (from 64 to 162) Eigen mode analysis (correction of DQs missing angle)
Lattice re-correction after BM sources (SB and 2PW) installation
Coupling correction (ev< 1pm.rad)
Dynamic aperture and injection efficiency studies (Still lower than model)
Automatic lifetime/losses optimizer (sextupoles, octupoles,skew scanning)
Db/b > 1.5% H ,
1.5% V,
Dh ~ 0.7 mm H,
0.7 mm V
IE 80%

## Slide 12: ESRF-EBS: Commissioning from 28/11 to 01/04
SR current ramping
Injection efficiency
30%
0.1%
20%
55%
5%
90 %
200 mA
Beamline commissioning
Winter shutdown
75%
28/11/2019
01/04/2020

## Slide 13: Lessons learned from the installation and the commissioning
Large benefit from phase 1 upgrade for the infrastructure and accelerator components
Capitalize on the expertise for installation and start-up gained on the existing facility prior upgrade (staff, procedures, control…)
Pre-assembly and anticipated tasks executed prior the shutdown
Design, procurement and installation procedures validated on the mockup
Activities concentrated on the storage ring during installation, limited activity for beamlines & infrastructure
Validation of control and tools on a simulator
Equipment test started as soon as possible, including control system
All systems (RF, diagnostics, power,..) operational and reliable from start of commissioning
Efficient beam position monitor and beam loss detectors available from the start of commissioning

## Slide 14: ESRF-EBS Impact of COVID-19 Pandemic
New cases
Deaths
USM
USM
But: 17-03/20 to 11/05/20: First lockdown in France (declared on 14/03/20) ESRF Closure  Stop operation
First
 28 Feb. 2020 plan: Machine ready for beamlines  Achieved
 03 March 2020 plan: Start of beamline commissioning  Achieved
Second
Third
But: 30/10/20 to 15/12/20: Second lockdown
03/04/21 to 03/05/21: Third lockdown
 Adaptation of the operation planning for users
 25 August 2020 plan: Start of user operation  Achieved
COVID-19 impacted the schedule as of 14 March 2020 (only), affecting mostly the beamline and user programme

## Slide 15: ESRF at the time of the COVID-19 Pandemic
Ensuring safe working conditions on site , strictly following French regulations
Objective: Restarting user service mode (USM) on 25 August 2020 with a maximum number of beamlines open
 ESRF KEPT FULLY OPERATIONAL FROM 25-08-2020 TO DATE!
16 March – 11 May
Closure, continuity plan, Teleworking.
Restart of the accelerator with minimum people onsite on 22 April,… but stopped due to a water leak….
CLOSURE
Less than 10 people on site
Less than 100 people on site
1st WAVE
12 May – 1 June
USM OPERATION
Back to USM
From 25 August
Back to USM Strict COVID-19 sanitary Telework privileged
RESUME OPERATION
Complete USM preparation
13 July – 24 August
2nd WAVE
Gradual
Increase of people on site
2 June – 10 July
2020
Normal operation of accelerators
Resume gradually storage ring & beamline commissioning, COVID-19 research
USM preparation
Telework privileged

## Slide 16: Impact of covid-19 for the operation
USM
From the start of the second lockdown to summer 2021, number of user shifts [blue] reduced (3&4 days /week).
Limited access to the site:
Opportunity to improve tools for remote control
Dedicated chat channels, Confluence, JIRA and Jlogbook have been actively used
Development shifts /interventions were often performed via video-conferencing Very efficient for short and fast support, including activities vith beamlines
MDT & Interventions
Tests with beamlines
COVID 19 first lockdown
2020
2021
August 2020
Beamline Commissioning
Machine
Commissioning
Second lockdown
Third lockdown
Video-conferencing and remote control are new operation tools for the future

## Slide 17: Return to Operation: Ongoing remote access experiments
IMPLEMENTING REMOTE ACCESS SOLUTIONS TO KEEP SCIENCE
AT THE FOREFRONT
New protocols for user programme operation, so that a majority of experiments can be conducted or followed up remotely
Implementation new solutions that allows users to interact remotely with beamline control software and tools
Implementation of large-scale sample mail-in solutions for user experiments
Remote data analysis with improved data transfer

## Slide 18: User statistics and activities – 25 August 2020 to 31 July 2021
43/44
43 out of 44 beamlines hosted user experiments
13 175
13 175 shifts delivered (105 400 hours)
1 872 user experiments
1 872
FIRST USM YEAR WITH THE NEW EBS STORAGE RING
A MILESTONE FOR THE X-RAY COMMUNITY
1262 fully remote (68%), 192 only one user (10%), and 418 with users (22%)
1 262

## Slide 19: Beam delivery from 25/08/2020 to 29/09/2021
 | 7/8 + 1 | Uniform | 32*12 | 28*12+1 | 62 bunch | 16 bunch | 4 bunch
(mA) | 196+4 * (192+8) | 200 | 150 * (200) | 125+3* (200) | 65* | 35* (90) | 20* (40)
Lifetime (hours) | > 22 | > 25 | > 22 | > 23 | ~ 14 | ~ 8 | ~ 5
(pm) * | 10 | 10 | 20 | 20 | 20 | 20 | 20
 | 7/8 + 1 | Uniform | 32*12 | 28*12+1 | 62 bunch | 16 bunch | 4 bunch
 | 196+4 * (192+8) | 200 | 150 * (200) | 125+3* (200) | 65* | 35* (90) | 20* (40)
Lifetime (hours) | > 22 | > 25 | > 22 | > 23 | ~ 14 | ~ 8 | ~ 5
 | 10 | 10 | 20 | 20 | 20 | 20 | 20
* Intensity limitation for timing modes due to mechanical weakness of the kicker ceramic chambers
* Vertical emittance artificially increased from 1 to 10 pm rad for an operational lifetime
* All timing modes delivered with a purity of 10-9 with cleaning process in the booster
Filling patterns

## Slide 20: Beam delivery since the start of USM
But also quiet time !
Some disturbed weeks !!
249 hours without a beam loss
29/09/2021
25/08/2020
Beam current

## Slide 21: Reliability
 | 2017 | 2018 | 2020 | 2021
 |  |  | EBS | EBS
Availability (%) | 98.3 | 98.5 | 96.1 | 98
Mean time between failures (hrs) | 64.3 | 104.3 | 46.0 | 73.4
Mean duration of a failure (hrs) | 1.11 | 1.60 | 1.80 | 1.46
Overall reliability comparable to that of the old source
Magnet power supply system was the most complex hardware to develop and commission
  Hot swap system under commissioning
  Human mistakes due to development (mostly at the beginning)
  Infrastructure (mains, cooling, doors)
Operation disturbed by a few long failures from sub-systems not linked to EBS design
  aluminum NEG coated ID vacuum chambers
  RF master source
  20 KV high voltage cable defect
  RF highly reliable
Number of failures 2021

## Slide 22: overview: beam current & Lifetime
Beam current [mA]
Lifetime [h]
200 mA
25 h
Average pressure [mbar]
USM
Commissioning
28/11/2019
29/09/2021
25/08/2020

## Slide 23: Vertical and horizontal Emittances from 25/08/2020 to 29/09/2021
Horizontal emittance diagnostics modified and calibrated during run 2020-06 and run 2021-1
 Typical today: 130 ± 20 pm.rad
Vertical emittance artificially blown up using white noise excitation up from 1 pm.rad to 10 or 20 pm.rad to get an operational lifetime
 Typical today: 10 pm ± 1 pm.rad
Vertical emittance
130 pm.rad
20 pm.rad
10 pm.rad
200 mA
Beam current
Horizontal emittance*
25/08/2020

## Slide 24: ESRF-EBS: parameter achieved
 | Design | Realized today
Total current | 200,90,40 mA | 200, 35, 20 mA
MTBF | > 30 h | > 70 h
Up-Time | 98% | 98 %
Injection Efficiency | > 90 % | > 80 %
Lifetime | > 20 h | > 25 h
 | < 140 pm rad | < 130±20 pm rad
 | 10 pm rad | 10 pm rad
Stability | < 0.05 | < 0.01
 | Design | Realized today
Total current | 200,90,40 mA | 200, 35, 20 mA
MTBF | > 30 h | > 70 h
Up-Time | 98% | 98 %
Injection Efficiency | > 90 % | > 80 %
Lifetime | > 20 h | > 25 h
 | < 140 pm rad | < 130±20 pm rad
 | 10 pm rad | 10 pm rad
Stability |  | 

## Slide 25: conclusion
Results:
Despite the impact of the Covid-19 pandemic, users recovered the beam on the scheduled day and with an adapted operation planning
Main performances achieved (beam current, beam modes, lifetime, emittances, stability)
Excellent reliability of the hardware
Delay in the beamline commissioning and upgrade programme
Additional operating and support tools and methods have emerged
Beamlines are now progressing and upgrading to take full benefit of the source
Users are starting to come back
Objectives for the machine:
Fine tuning of beam parameters
Implementation of the hot-swap system for the power supplies
Reduce injection perturbation and go back to injection from every 1hour to every 20 mn
Nominal beam current in time-structured modes

## Slide 26: Many thanks for your attention